## Tabelle1
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contigency Plan | Responsible | Status | Last modified date | Comments
1 | Technical | Supabase becomes unavailable | 1 | 4 | 4 | Use self-hosted development and production environments with version control | Supabase newsfeed | Use backuped database setup files and move postgres functions to new solution. | Magnus Henning | Closed | 2023-06-29 | Local version of supabase on our computers
2 | Technical | Flutter becomes deprecated | 1 | 9 | 9 | We die screaming if it comes to it | Flutter newsfeed | Search Flutter alternative, if none exists every artifact (web, android, IOS) has to be developed on ist own. | Moritz Mueller | Open | 2023-06-29
3 | Project | Two or more call in sick simultainiously | 3 | 4 | 12 | Everyone has the essential knowledge to continue. No CORONA!!!!! Get vacinated | Flu session, new Corona version, sickly look of employees, coughing, etc. | home office, task reassignment | Jonas Nuber | Closed | 2023-06-29 | Project closed
4 | Business | Unprofitable pricing model | 2 | 6 | 12 | Get informed, run ads | Not enough or no profit after 1 month | Changes in ads, pricing model or the products feature | Tim Schöndorf | Open | 2023-06-29
5 | Legal | Unexpected data regulation changes | 1 | 5 | 5 | Capability for our system to react and change | New legal paper, discussion in progress | Remove problem module from production | Tim Wortmann | Open | 2023-06-29